## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Setup React project structure and configure routing for all dashboards (Home, Static, Streaming, ML, Network, Reports). | MUST HAVE | React, TypeScript | Avinash S,Manisha Sadurla | 3 - Completed
S1 | S1 | US-002 | Implement core layout components (Sidebar, Navbar, Page Container) with responsive UI. | MUST HAVE | Tailwind CSS, shadcn/ui | WALI SNEHA CAROLYN | 3 - Completed
S1 | S1 | US-003 | Deploy initial CyberShield AI application to Vercel. | MUST HAVE | Vercel Deployment | Rajeswari Rodda | 3 - Completed
S2 | S2 | US-004 | Develop interactive Recharts components (Line, Pie, Bar, Area charts). | MUST HAVE | Recharts Library | Ashutosh Paswan | 3 - Completed
S2 | S2 | US-005 | Implement Static Data Dashboard (Dataset Upload, Analyze Data, Export Results). | MUST HAVE | File Parsing / JSON Handling | Avinash S,Manisha Sadurla | 3 - Completed
S2 | S2 | US-006 | Build Streaming Data Dashboard with real-time data simulation (Pause, Resume, Refresh). | SHOULD HAVE | Event Simulation | Avinash S,WALI SNEHA CAROLYN | 3 - Completed
S3 | S3 | US-007 | Integrate ML Dashboard with model training and accuracy comparison charts. | MUST HAVE | ML Training Logic | Avinash S,Rajeswari Rodda | 3 - Completed
S3 | S3 | US-008 | Implement VPN/WiFi Dashboard (Network Status, Bandwidth Chart, Scan Network). | MUST HAVE | Network Logic Simulation | PRATIK ABHANG | 3 - Completed
S3 | S3 | US-009 | Build Threat Reports Module (Generate Report, Download File, Trend Charts). | MUST HAVE | Report Generator / Recharts | Rajeswari Rodda | 3 - Completed
S4 | S4 | US-010 | Integrate all dashboards together and perform full system testing & bug fixing. | MUST HAVE | All Features | Entire Team | 3 - Completed
S4 | S4 | US-011 | Prepare documentation (Agile Log, Architecture, Screenshots) and Final PPT. | MUST HAVE | Project Complete | Avinash S | 3 - Completed

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 103.5 | 15 | 16.5 | 13.5 | 13.5 | 12.5 | 12 | 9.5 | 10.5 | 0.5 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TASK-001 | Set up hosting & backend infra | 2025-10-12 | 2025-10-14 | Avinash,Manisha sadurla | Deployment | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TASK-002 | Pre-process static dataset | 2025-10-12 | 2025-10-16 | WALI SNEHA CAROLYN | Data Processing | Completed | 7 | 2 | 1.5 | 1.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TASK-003 | Dashboard UI layout & style | 2025-10-14 | 2025-10-18 | Rajeswari Rodda | UI Development | Completed | 6 | 0 | 2 | 2.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TASK-004 | Train ML model (Iteration-1) | 2025-10-18 | 2025-10-20 | Ashutosh Paswan | Model Training | Completed | 4 | 0 | 0 | 0 | 0 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TASK-005 | Architecture + Agile docs | 2025-10-20 | 2025-10-22 | Avinash,Manisha sadurla | Documentation | Completed | 5 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0
SPRINT 2 BACKLOG
US-007 | TASK-001 | Implement interactive charts (all dashboards) | 2025-10-26 | 2025-10-30 | WALI SNEHA CAROLYN | UI Integration | Completed | 7.5 | 3 | 2.5 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TASK-002 | Rule-based chatbot logic | 2025-10-26 | 2025-10-31 | Rajeswari Rodda | Logic Dev | Completed | 8 | 1 | 1.5 | 1.5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TASK-003 | Admin panel UI for offline dataset upload | 2025-11-01 | 2025-11-04 | Pratik Abhang | UI Dev | Completed | 7 | 0 | 0 | 0 | 0 | 3 | 2.5 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TASK-004 | Backend optimization for large files | 2025-11-04 | 2025-11-07 | Avinash | Backend | Completed | 8 | 0 | 0 | 0 | 0 | 0 | 1 | 2.5 | 4 | 0.5 | 0 | 0 | 0 | 0
SPRINT 3 BACKLOG
US-012 | TASK-001 | Implement IP/API scanner with external APIs | 2025-11-12 | 2025-11-15 | Manisha Sadurla,Rajeswari Rodda | API Integration | Completed | 7 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | TASK-002 | Prioritized Action Plan logic | 2025-11-12 | 2025-11-15 | Manisha Sadurla | Logic Dev | Completed | 6 | 1 | 0 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | TASK-003 | UI for scanner results + recommendation panel | 2025-11-16 | 2025-11-19 | Avinash s,WALI SNEHA CARAOLYN | UI Dev | Completed | 7 | 0 | 0 | 1 | 1.5 | 3.5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | TASK-004 | Fine-tune ML model + implement error logs | 2025-11-19 | 2025-11-21 | Avinash S,Rajeswari Rodda | Model Refinement | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
SPRINT 4 BACKLOG
US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Effort | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14
US-017 | TASK-001 | Final end-to-end bug fixing | 2025-11-24 | 2025-11-28 | Entire team | Final Testing | Completed | 7 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-018 | TASK-002 | Final documentation (Agile + Architecture) | 2025-11-28 | 2025-12-02 | Avinash S | Documentation | Completed | 8 | 0 | 0 | 1.5 | 2 | 3 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-019 | TASK-003 | Final PPT and project demo script | 2025-12-03 | 2025-12-05 | all | Presentation | Completed | 6 | 0 | 0 | 0 | 0 | 0 | 1 | 2.5 | 2.5 | 0 | 0 | 0 | 0 | 0

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | S1 | 2025-10-06 | 2025-10-17 | Avinash S | Taking lead in dashboard flow setup and UI framework structure. | Delaying integration of different chart components. | Building interactive charts, improving responsiveness, and ensuring component-level consistency. | Entire dashboard foundation + chart integration completed smoothly under her lead.
2 | S1 | 2025-10-06 | 2025-10-17 | WALI SNEHA CAROLYN | Working actively on deployment using Render and fixing hosting issues. | Depending on temporary local deployments. | Improving frontend integration & solving rendering inconsistencies. | Successful deploy on Render + stable environment setup.
3 | S2 | 2025-10-20 | 2025-10-31 | Manisha Sadurla | Performing systematic data preprocessing for static dashboards. | Waiting for others’ datasets to start working. | Cleaning datasets, handling nulls, and smoothing preprocessing pipeline. | Clean dataset delivered for dashboard use + static data dashboards progressed.
4 | S2 | 2025-10-20 | 2025-10-31 | Rajeswari Rodda | Improving documentation formatting & UI styling alignment. | Redoing layouts repeatedly. | Maintaining consistent documentation + styling. | Final documentation pages & threat report formatting improved.
5 | S3 | 2025-11-03 | 2025-11-10 | Ashutosh Paswan | Coordinating with model training workflow and dashboard wiring. | Manually adjusting model variables repeatedly. | Assisting in model flow + linking output to UI. | Model workflow stabilized and connected to dashboard sections.
6 | S3 | 2025-11-03 | 2025-11-10 | PRATIK ABHANG | Expanding work on network/VPN scan dashboard components. | Overfocusing on UI instead of backend logic. | Developing scanning logic + integrations. | VPN & Network scanning UI + functional logic implemented.
7 | S4 | 2025-11-11 | 2025-11-17 | WALI SNEHA CAROLYN | Performing detailed streaming dashboard checks. | Last-minute fixes without testing. | Validating outputs & ensuring stability. | Streaming analysis tested and validated for stable use.
8 | S4 | 2025-11-11 | 2025-11-17 | Avinash S | Improving report generation layout & error notifications. | Relying on default UI templates. | Layout structuring & clean alert messages. | Final report generation UI made clean, readable & error-free.

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 4 | Confusion in aligning UI layouts with the main dashboard design because multiple chart components behaved differently. | Avinash S conducted a short walkthrough of the UI structure and finalized the component layout standards.
S1 | Day 7 | Deployment on Render kept failing due to environment variable conflicts and missing build configurations. | WALI SNEHA CAROLYN resolved the issue by restructuring the env setup and configuring proper build commands.
S2 | Day 12 | Inconsistent cleaned datasets caused errors during static dashboard rendering. | Manisha Sadurla standardized the preprocessing script and regenerated unified datasets.
S2 | Day 15 | Difficulty in adjusting the documentation format to maintain uniform font, spacing, and threat-report structure. | Rajeswari Rodda created a proper documentation template and guided the team on structuring sections.
S3 | Day 20 | Admin Panel model-training workflow crashed when switching between file uploads and manual input mode. | Avinash S and WALI SNEHA CAROLYN debugged the workflow and added conditional checks + fallback logic.
S3 | Day 24 | Network/VPN scanner dashboard showing delayed fetch results due to heavy API execution. | Ashutosh Paswan optimized the scanning logic and added asynchronous handlers.
S4 | Day 33 | Streaming dashboard logic breaking whenever rapid log updates were received. | PRATIK ABHANG fixed the validation pipeline and coordinated with the team to stabilize streaming inputs.
S4 | Day 38 | Report generation section had missing styles, misaligned headers, and inconsistent alert messages. | Avinash S and Rajeswari Rodda restructured the report layout and standardized all alert/error message formats.